Final Report: Work-In-Process Buffer Design Methodology for Scheduling Repetitive Building Projects

Vicente González and Luis F. Alarcón

Abstract

Variability is one of the factors with the largest negative impact in construction projects, which can induce dynamic and unexpected conditions, unsteadying project objectives and obscuring the means to achieve them. A common practice in construction to protect production systems from variability is the use of buffers (Bf). However, current buffering practices in construction are characterized by the intuition and informality leading to poor control of variability. For overcoming these limitations, this research proposes a Bf design methodology based on Work-In-Process (WIP) for scheduling repetitive building projects at tactical and strategic levels. At tactical level, the methodology uses Simulation-Optimization (SO) models to design optimum WIP Bf sizes by different project objectives. Two home building projects implementing the methodology at this level were studied. As a result, improvements on labor productivity and project cost were obtained. At strategic level, a multiobjective model to apply the Bf design methodology was developed, demonstrating its advantages through a project scheduling example. Finally, the impacts of applying WIP Bf strategies based on Lean Production principles are addressed.

Key Words: Buffer Design, Lean Production, Work-In-Process, Simulation-Optimization, Variability.

# Introduction

Variability is one of the factors with the largest negative impact in construction projects. It can induce dynamic and unexpected conditions, unsteadying project objectives and obscuring the means to achieve them. To understand its effect over production processes, Hopp and Spearman (2000) distinguished two kinds of variability in manufacturing systems: (i) the time process of a task executed at a workstation and (ii) the arrival of jobs or workflow at a workstation. Koskela (2000) proposes a similar classification to variability in construction systems, where the processes duration and the flow of preconditions for executing construction processes (e.g., space, equipment, workers, component and materials, among others) are understood as variable production phenomena. From a practical standpoint, construction practitioners everyday observe the variable behavior of project environment through production rates, labor productivity, project schedule and budget, etc., confirming theoretical statements addressed above.

Several researchers have shown that variability is a well-known problem in construction projects, which leads to a general deterioration of project performance on dimensions such as: cycle time (Alarcón and Ashley, 1999; Ballard, 1993; González and Alarcón, 2006; Shen and K.H. Chua, 2005; Tommelein et al, 1999), labor productivity (Thomas et al, 2002, 2003), project cost (Ballard and Howell, 1994), planning efficiency (Alarcón et al, 2005; Howell and Ballard, 1995), among others. A way to deal with variability impacts in production systems is the use of buffers (Bf). By using a Bf a production process can be isolated from the environment and the processes depending on it (Koskela, 2000). Bf can avoid loss of throughput, wasted capacity, inflated cycle times, larger inventory levels, long lead times and poor customer service shielding a production system against variability (Hopp and Spearman, 2000). Hopp and Spearman (2000) define three generic types of Bf, which can be understood in construction as:

- Inventory: These are in-excess stock of raw materials, Work in Progress (WIP) and finished goods, categorized according their position and purposes in supply chain (Polat et al, 2007).

- Capacity:   Allocation of labor, plants and equipment capacity in excess so that they can absorb actual production demand problems (Horman, 2000).

- Time: Reserves in schedules as contingencies used to compensate adverse effects of uncertainty. Also, Float may be understood as Time Bf since protects critical path from time variation in non-critical activities.

Traditional approaches to project management are mainly based on assumptions that do not consider the project complexity and its non-linear nature (Bertelsen, 2003). McCray et al (2002) states that poor systematic rules or heuristics to deal with the dynamic nature of projects lead to poor decisions. One of the biggest problems in project management is the use of intuition and experience, which promotes superficial and informal analysis (Laufer, 1994).  In construction, current buffering practices follow an intuitive and/or informal pattern similar to traditional project management, leading to poor variability control (Alarcón and Ashley,1999; Alarcón and Calderón, 2003; Alves and Tommelein, 2003; Arbulu et al, 2003; Bing et al, 1999; CII, 1988; Ford, 2002; Goldratt, 1997; González et al, 2004; González and Alarcón, 2006; Horman, 2000; Howell et al, 2001; Kim and De la Garza, 2003; Leach, 2003; Park and Peña-Mora, 2004; Rojas and Aramvareekul, 2003; Tommelein, 1998; Tommelein et al, 1999; Thomas and Arnold, 1996).

Recently, several researchers and practitioners have proposed new Bf approaches to manage variability in construction (Alarcón and Ashley, 1999; Ballard, 2000; Howell et al, 1993; Bashford, 2003; Horman, 2000; Goldratt, 1997; Tommelein et al, 1999, among others), which have allowed in part to avoid the informal and intuitive way of designing and managing Bf in construction. They have contributed to the growing progress toward the understanding of variability and buffer management in construction; however, it is difficult to find practical buffering approaches that can be applied in construction projects (Park and Peña-Mora, 2004).

This paper proposes the use of Work-In-Process (WIP) as Bf for repetitive building projects, to overcome the limitations addressed above. In construction, WIP can be intended as the difference between cumulative progress of two consecutive and dependent activities or processes, which characterizes work units ahead of a crew employed to perform work. This definition of WIP is more visible in repetitive projects where processes are repeated continuously (e.g. high-ways, railways, pipelines, sewers, etc.) or in discrete repeated units (e.g. high-rise, multistory, and home buildings, etc.) (Ipsilandis, 2007).  WIP can be used as type of Inventory Bf (Hopp and Spearman, 2000) and this research proposes its application in repetitive projects by the following reasons:

- WIP Bf can decrease the impact of variability of production rates on repetitive construction processes that succeed one another in linear sequences (Ripple Effect) (Alarcón and Ashley, 1999; Tommelein et al, 1999).

- Researches that have studied or provided some approach to design WIP Bf in repetitive projects, do not also provide practical methodologies to construction (Alarcón and Ashley, 1999; Alves and Tommelein, 2004; Bashford et al, 2003; González, et al, 2006, Howell et al, 1993, Lee et al, 2003; Park and Peña-Mora, 2004; Sakamoto, et al, 2002; Srisuwanrat and Ioannou, 2007; Tommelein, 1998, Walsh et al, 2007; among others).

- Recently, empirical evidence has showed that “Lack of WIP” is a central problem in construction project planning (included repetitive projects) (Alarcón and Calderón, 2003). This evidence suggests that it is necessary to improve the use of WIP in construction projects.

- Cyclical behavior of processes in repetitive projects made more suitable to design WIP Bf in this type of projects.

Theoretically, this methodology is supported in Lean Production principles synthesized for construction in the following ones (Koskela, 2000): i) Reduce the share of non value-adding activities (also called waste, e.g., wait times), ii) Increase the efficiency of the value-adding activities (e.g., process duration), and iii) Reduce variability. In addition, they are focused under a main lean objective: to optimize the performance of a production system as a whole (Womack and Jones, 1996).

The use of WIP Bf, however, is controversial from a Lean Production standpoint since the lean ideal suggests zero inventories or non-buffer in production systems (Womack and Jones, 1996). But, in a practical sense “a production system without WIP means a production system without throughput”. Also, Hopp and Spearman (2000) state that pull mechanism in a production system does not avoid the use of buffers. In contrast, if production systems use large WIP Bf to ensure throughput, this means to increase cycle times. As a result, it appears a ‘balance problem’ among the use of WIP Bf to reduce variability impacts and production system performance.

In this research, to solve this problem Simulation-Optimization (SO) modeling is used, designing optimum WIP Bf Sizes according to different project objectives. Computer simulation has been applied by several researchers in construction with different scopes and application contexts (Agbolus and AbouRizk, 2003; Al-Battaineh and AbouRizk, 2006; Halpin, 1977; Martínez, 1996; Vanegas et al, 1993, among others). Several researchers have used simulation techniques to model the effect of buffering strategies in production systems or supply chains in construction (Alarcón and Ashley, 1999; Alves and Tommelein, 2004; Arbulu and Tommelein, 2002; Horman, 2000; Lee et al, 2003; Tommelein, 1998; Walsh et al, 2002, among others). But this trade-off has not been solved efficiently and they only address specific cases. The first application to model Bf in construction by using SO was proposed by González et al (2006). Later, Srisuwanrat and Ioannou (2007) developed a similar SO approach to model Bf in a construction scheduling context. However, both researches fall to apply in real cases their approaches and to propose a practical method to design Bf in construction.

The main objective of this research is to develop a sound and practical methodology to design WIP Bf using SO modeling in repetitive building projects, showing its advantages in different construction production scenarios. In doing so, methodology is applied in construction scheduling process at tactical and strategic levels. Al tactical scheduling level, methodology designs WIP Bf by using SO models.  At strategic scheduling level, a multiobjective model to design WIP Bf is developed from the proposed SO approach and using concepts of Pareto Front.

# Research Methodology

The research methodology consists on four stages: Definition of Simulation-Optimization (SO) approach, Development of WIP Bf design methodology at tactical scheduling level, Development of WIP Bf design methodology at strategic scheduling level, and Application of WIP Bf design methodology in scheduling process of repetitive building projects. First, a discrete event simulation (DES) modeling architecture is proposed, which is used as basis to elaborate SO concepts in the WIP Bf design methodology. Second, the main steps of the WIP Bf design methodology at tactical scheduling level are developed including: construction of simulation models for repetitive processes, SO modeling to design optimum WIP Bf sizes and development of buffered construction schedules at tactical level. Third, the WIP Bf design methodology at tactical scheduling level is developed based on the proposed SO approach and Pareto Front concepts, leading to multiobjective model to design WIP Bf. The main steps including: development of abacus for multiobjective model for different project goals and variability levels, sensitivity analysis and selection of WIP Bf sizes according to project preferences, and development of buffered construction schedules at strategic level. At last, project construction applications are analyzed. At tactic scheduling level, two real home building projects (cases study) are studied, collecting and analyzing their on-site impacts. At strategic scheduling level, a repetitive building project example is used.

# Scheduling Approach to design WIP Bf

Construction planning is a fundamental and challenging activity in the management and execution of construction projects. It involves the choice of technology, the definition of work tasks, the estimation of the required resources and durations for individual tasks, and the identification of any interactions among the different work tasks. A good construction plan is the basis for developing the budget and the schedule for work (Hendrickson and Au, 1989). Definition of work tasks or processes, and their individual durations and relationships with other ones characterizes construction scheduling, being a central part within construction planning.

Ballard and Howell (1998) define three levels for construction planning: Initial or Strategic planning (long term period), Look Ahead or Tactical planning (breakout of Master Plan in a medium term period), and Work or Operational planning (short-term period), which are progressively more detailed from top to bottom in dimensions such as: budget and construction schedule, definition of work methods and resources, work and resources coordination and control, work completions and deliveries, etc. Construction scheduling can be intended according the planning levels: Strategic, Tactical and Operational scheduling, which have more detailed time windows and definition of processes production features (processes duration, kind of precedence relationships, etc.) from top to bottom.

In this research, the WIP Bf design methodology acts on tactical and strategic scheduling levels, being the tactical level the basis to develop the strategic level. The operational level is part of ongoing research, which is currently investigated. The strategic and tactical levels of the methodology work over the design dimension of WIP Bf, and the operational level works over the management dimension of WIP Bf on-site.

# Conceptual Understanding of WIP Bf

In the context of repetitive projects, WIP Bf can be characterized by using Line of Balance (LOB). Figure 1 shows the LOB for ‘n’ processes in a repetitive project with its different production parameters. The purpose to develop a conceptual model for WIP Bf is to understand what variables are involved in different production scenarios and how they impact the size of WIP Bf.

The variable nature of construction processes suggests that a deterministic value for processes duration or production rates is not realistic. From Figure 1, let repetitive processes P1, P2,…, Pn-1, Pn with average production rates and standard deviation called m1, m2,…, mn-1, mn (units/day) and SD1, SD 2,…, SDn-1, SDn (units/day), respectively. Production rates (mi) for each process is an average value with a certain variation (SDi). This variable behavior can be captured mathematically by means of probability density function (PDF) of duration by production unit or production rate by day (See Figure 1.a and 1.b). Figure 1.a shows the duration PDF (f(x)), with an expected duration by production unit (μD) and a certain standard deviation (σD) for actual cumulative progress. On the other hand, Figure 1.b shows production rate PDF (f(y)), with an expected progress by day (unit production rate) (μR) and a certain standard deviation (σPR) for actual cumulative progress.

Figure 1. Conceptual Model for WIP Bf: a) Unit Duration PDF, and b) Unit Production Rate PDF.

Commonly, variability of a process (duration or production rate PDF) impact over succeeding processes. For instance, P1 variability impacts over P2,  P2 variability impacts over P3, an so on, being the production variability a cumulative effect from upstream processes to downstream processes in repetitive production systems (Ripple Effect). Previously, some researchers had been studied the Ripple effect in repetitive processes  in construction (Alarcón and Ashley, 1998; Tommelein, 1998; Tommelein et al, 1999) and how the use of WIP Bf decreases this effect, isolating and protecting processes from upstream processes variability.

The location and size of WIP Bf for repetitive project can be seen in Figure 1 (a or b). Let WIP Bf 1,2, WIP Bf2,3,…,WIP Bfn-1,n which have the corresponding Time Bf called T Bf 1,2, T Bf2,3,…,T Bfn-1,n, respectively. The main assumption related to location and size of WIP Bf within production processes is that they are restrictions applied only at the beginning of processes, and they could change during progress evolution of work between processes. Considering the production nature of construction projects, WIP Bf size could assume one of the following states: i) Minimum WIP Bf (MWIP Bf) is the minimum amount of work units ahead of a crew, from which it can perform its work avoiding any technical problem (e.g., to avoid crew congestion). This is a boundary condition for modeling. Its related Time Bf is defined as MT Bf; ii) The Initial WIP Bf (IWIP Bf) is the amount of work units ahead of a crew allocated at the beginning of the downstream processes to protect them from the process duration or production rate variability of the upstream processes (e.g., to avoid waiting time by lack of production units to perform work). Its related Time Bf is defined as IT Bf.

The remaining production parameters showed in Figure 1 are:

CTi=TP/mi                                                                                                                                Equation 1

Where:

CTi= Cycle Time for process i, (days), i=1…n.

And:

TCT= Total Cycle Time for cluster of n processes, (days).

TP= Total production, (units).

# WIP Bf Design using Simulation-Optimization

## Simulation Architecture

Production systems in construction are complex, dynamic and variable. These features make production systems in construction suitable to be modeled through simulation, which ‘is a numerical model evaluated using a computer, where data are gathered in order to estimate the desired true characteristic of the model’ (Law and Kelton, 2000).

In this research, a discrete-event simulation (DES) modeling is applied in order to design WIP Bf. DES describes systems evolving over time where state variables change instantaneously at separate points in time (Law and Kelton, 2000), being an appropriate simulation approach to represent the common behavior of construction processes in repetitive building projects. In addition, construction processes are simulated as terminating simulation without warming up period or initial data deletion to mimic their real production start conditions (González et al, 2006).

DES software called Extend™ was selected to perform simulation modeling given its powerful features to visualize and to handle highly dynamic and complex system (Extend v6 User’s Guide, 2002). Figure 2 shows the simulation modeling architecture proposed in this paper, which is made up by two kinds of hierarchical blocks: processes and WIP Bf. Inside these blocks, there are individual blocks, logical decision processes and stochastic inputs (i.e. process duration or production rate). This simple precedence relationship between processes is assumed due to many real situations in repetitive building projects are performed as group of linear and dependent processes (Parades of Trades) subject to impact of variability and Ripple Effect (Tommelein et al, 1999).

Figure 2. Simulation Modeling Architecture.

Extend™ is based on a simulation strategy called Process Interaction (PI) where entities flow throughout the system (Hooper, 1986), flowing as integer units in production systems simulated with Extend™. For proposed simulation modeling architecture, work units as houses or floors for building projects are the entities flow throughout the system from “INPUT” to “OUTPUT”. At the beginning, work units flow from “INPUT” to “PROCESS 1” block, where work units are either accumulated according to some defined production rate PDF for an unitary time (e.g., one day), or one work unit is processed over a duration basis according to some defined process duration PDF in the process block. Finally, the selection of either production rate or process duration PDF for each process block in the simulation models depends on the preferences of the project decision makers.

Once work units have been processed, they are accumulated in “WIP BUFFER” block until the specified amount of work units is reached, i.e. MWIP Bf or IWIP Bf (see section 4). Finally, the released units by “WIP BUFFER” are processed in “PROCESS 2” and released to leave the system by “OUTPUT”. The production cycle is completed when every work units have been processed by all process hierarchical blocks.

## Simulation-Optimization to design WIP Bf

IWIP Bf are the production decision variables to explore against project performance by using simulation. So, the balance problem between WIP Bf size and project performance (addressed in section 1) pushes to get optimum sizes for IWIP Bf according to project objectives. In order to find the optimum IWIP Bf sizes, SO modeling is used. In SO models, ‘the simulator represents a function ((x1,…,xn) for some input parameter vector x = (x1,…,xn). The optimization goal is to find min x(WE[((x)] or max x(WE[((x)], where the response E[((x)]is the expectation of ( (x) and W is a feasible range for the parameters’ (Buchholz and Thümmler, 2005). Extend™’s Evolutionary Optimizer Module is applied to optimize the IWIP Bf sizes. This Extend™’s module is based on evolutionary algorithms called Evolutionary Strategies (ES). The ES are algorithms similar to Genetic Algorithms that mimic the principles of natural evolution as a method to solve parameter optimization problems (Carson and Maria, 1997).

According to the production parameters analyzed in Figure 1, the project objectives to find the optimum IWIP Bf size are:

- Minimize Total Cycle Time (Min TCT): Decrease the project total time.

- Minimize Total Cost (Min TC): Decrease the project total cost.

- Maximize Average Total Production Rate (Max ATm): Increase the average project production rate of n processes.

Time and cost are usually project objectives utilized by decision-makers to define the better project production strategies. Additionally, ATm was chosen to analyze high levels of continuous resource utilization, i.e. crew or equipment working without interruptions and stoppages (Srisuwanrat and Ioannou, 2007), when this objective is maximized (having impacts on time and cost, respectively).

The following general cost model to Min TC is used:

TC= Direct Cost + Indirect Cost                                                                                               Equation 2

Direct Cost=DC=                                                 Equation 3

Where:

MUCi= Material Unit Cost for process i, ($/unit), i=1…n.

LDCi: Labor daily cost for process i, ($/day), i=1…n.

EqDCi: Equipment daily cost for process i, ($/day), i=1…n.

And:

Indirect Cost=IC=                                                                                 Equation 4

Where:

SPCi= Supervision cost for process i ($),

DOC: Daily Overhead Cost for a construction project, ($/day), i=1…n.

The expression to Max ATm is as:

ATm=                                                                                                                                Equation 5

Finally, the solution space where optimum IWIP Bf size can be searched is given by the following restrictions:

MWIPBf1,2 ≤ IWIPBf1,2 ≤ TP,…, MWIPBfn-1,n ≤ IWIPBfn-1,n  ≤ TP

# Multiobjective Model to Design WIP Bf

In this paper, the design of WIP Bf is intended as a multiobjective decision process to avoid the ‘balance problem’ with performance objectives. Furthermore, it should be practical to promote its penetration among construction practitioners. Both statements can be attained by using simple analytic models with multiple objectives as nomographs or abacus (e.g. similar to commonly used in hydraulic or hydrologic engineering), bounding them by means of SO outputs depending on project objectives.

To get a rationale solution for analytic models, Pareto Front concepts are introduced. The notion of Pareto Front was generalized by Vilfredo Pareto in the 19th century, being a currently accepted tool for comparing solutions in multiobjective optimization that have no unified criterion with respect to optima (Zheng et al, 2004), helping to find good compromises or ‘trade-offs’ rather than a single solution. For instance, in construction the common Cost-Time trade-off problem has been faced using Pareto Front concepts by several researchers (Feng et al, 1997; Yang, 2005; Zheng et al, 2004; Zheng and Thomas, 2005; among others). Figure 3a shows a common Cost-Time trade-off using Pareto Front, where points a1,…, an are resources mix for a project (corresponding to production strategies as crew sizes, equipment, methods, and technologies to perform processes). Points a1, a3, a5, a7, and a9 are along Pareto Front line and represent non-dominated solutions, e.g. point a3 is on this line since is a non-dominated solution, being partially better than another solution as point a2 or a4. Points a1 and a9 represent optimum points for minimum Time and Cost, respectively, and they help to bound the whole Pareto Front Line (Zheng et al, 2004). Finally, a determined solution will depend on project decision-makers preferences, e.g. if project should save time will use more productive equipment and/or hiring more workers, but the cost could increase and vice versa (Feng et al, 1997).

Another approach could use differences between expected (in this case, planned) and actual estimations as is shown in Figure 3b. ∆Cost and ∆Time are the difference between actual and expected budget and schedule, respectively. How a construction process can be understood as a variable (or stochastic) phenomenon, it is reasonable to intend that such differences will exist. On the other hand, Figure 3c shows that the same Cost-Time trade-off can be stated for different WIP Bf sizes (WIP Bf1,…, WIP Bf5), but keeping constant resources mix. However, the purpose of developing practical abacus is related to their capability of generalization. A given project cost frame is a function of specific project characteristics, changing from project to project. Then, it is a difficult task to generalize abacus for repetitive projects when one of its variables is cost-based. Figure 3d describes a complementary approach replacing ∆Cost by ∆ATm defined as the difference between expected and actual average production rates for processes contained in a repetitive project. In general, production rate is a more flexible performance objective commonly found in construction processes. ∆Time is replaced by ∆TCT (used nomenclature in this paper) and extreme points on Pareto Front Line, WIP Bf1 and WIP Bf5, represent the minimum ∆TCT and ∆ATm, respectively.

The general frame of abacus allows to design WIP Bf for repetitive building projects with a number of processes ranged from 2 to n processes, defining a constant WIP Bf size between processes. However, a decision-maker could choose a WIP Bf size not only by its impact on time and production rate, but also in project cost. In this research, it is assumed that the WIP Bf size that minimizes ∆Cost is between ∆TCT and ∆ATm (next sections show the truthfulness of this assumption). Then, a decision-maker can take the abacus showed in Figure 3d and to develop sensitivity analysis for ∆TCT, ∆ATm and ∆Cost or ∆TC (TC was defined in this paper for project cost), and to choose the optimum WIP Bf size according its preferences.

Figure 3. Pareto Front curves: a) Cost-Time trade-off, b) ∆Cost-∆Time trade-off, c) ∆Cost-∆Time trade-off for WIP Bf, and d) ∆Tm-∆TCT trade-off for WIP Bf.

To evaluate the impacts of WIP Bf size using abacus (Figure 3d), the expressions for ATm, TCT and TC are as:

Actual ATm= Planned ATm×(1-∆ATm)                                                                                     Equation 6

Actual TCT= Planned TCT×(1+∆TCT)                                      Equation 7                                           (TCT computed over critical path of construction schedule at strategic level).

Actual TC=  +                    Equation 8

Replacing Equation 1 in Equation 8:

Actual TC= +       Equation 9

If it is regarded actual production rate by process i as:

Actual mi=Planned mi×(1-∆ATm)                                                                                         Equation 10

And replacing Equation 7 and 10 in Equation 9, Actual TC is as:

Actual TC= +                                                                          Equation 11    (TC computed over every processes of construction schedule at strategic level).

It is necessary to notice that there will be as many Pareto Front line as variability levels, from which decision-makers to design WIP Bf. Variability levels will be another production variable to choose. In this research, the variability levels for processes are regarded as the Coefficient of Variation (COV) for process duration computed as the ration between σD and μD (See Figure 1a for nomenclature).

# Methodology to design WIP Bf at Tactical and Strategic Scheduling Levels

This section explains how to use SO and multiobjective models to design WIP Bf, in a construction scheduling context for repetitive building projects. The natural sequence of methodology development should be from top to bottom of scheduling process (from strategic to operational). Nevertheless, the focus research was initially conducted from tactical scheduling standpoint where SO modeling is better suited. Once, the SO modeling framework is validated and its robustness is demonstrated through real construction projects applications, strategic and operational scheduling levels are studied. Strategic scheduling level by using multiobjective models to design WIP Bf is analyzed. Operational scheduling level to design WIP Bf will be addressed in next articles.

## Tactical Design of WIP Bf

This level of the methodology for WIP Bf design is explained in Figure 4.

Figure 4. Methodology to design WIP Bf at tactical scheduling level.

## Strategic Design of WIP Bf

For repetitive building project, the strategic scheduling process produces initial estimations of processes duration or production rates. Due to the processes are performed as ‘Parade of Trades’ is usual to consider the pace of construction processes as a constant magnitude, leading to also estimate duration processes or production rates as constant magnitudes for the whole production system. So that, this assumption in the multiobjective model to design WIP Bf should produce constant IWIP Bf sizes for all processes. Besides, ∆TCT and ∆ATm are estimated from processes contained in critical path. In contrast impacts on costs (∆TC) are estimated from all processes since IWIP Bf sizes are transferred to the complete system.  Figure 5 describes methodology at this level in detail.

Figure 5. Methodology to design WIP Bf at strategic scheduling level.

# Project Application

## Tactical Level Application

Two home building projects located in Santiago-Chile were studied as case studies at this level. This research was performed between June and December during 2006, being part of an ongoing research that explores production strategies based on WIP Bf (González et al, 2006). Table 1 shows the general production characteristics of both case studies.

Table 1. Production Characteristics of the Case Studies.

Project Kind of production units Measurement of production units Type of Production Units a Number of production units Average area by production unit (m2) Number of analyzed processes Precedence Relationship Planned Total Cycle Time (days)b Planned Total Cost ($)c A Houses Units 1 32 180 5 Finish-Start 58 56,883.80 B 2 85 4 35 31,173.3 a Given for simulation effects. b Execution Time for analyzed processes package. c Approximated Budget in U.S. dollars for analyzed processes package.

### Case Study A

Step 1 and 2: Table 2 shows the planned schedule parameters and total costs of selected processes package. Equipment and supervision costs are not regarded. The MWIPBf size for all processes is equal to 0.6 units.

Table 2. Planned Production and Cost Parameters for Case A.

Planned Production Parameters and Direct Costs Planned Indirect Costs Process Type of Process MUCi ($/unit) TP (units) mi (units/day) CTi (days) LDCi ($/day) DC ($) DOC ($/day) TCT (days) Overhead ($) P1 DryWall Ceeling $199.4 32 0.6 54.0 $101.5 $11,794.7 $100.0 58 $5,800.0 P2 Partition $245.8 32 0.6 54.0 $71.6 $11,682.8 Total (2) $5,800.0 P3 Doors Installation $177.7 32 0.6 54.0 $57.9 $8,774.6 P4 Waterproof $136.6 32 0.6 54.0 $67.7 $7,982.2 P5 Kitchen Floor (Ceramic) $179.5 32 0.6 54.0 $95.7 $10,849.6 Total (1) $51,083.8 Total (1) + (2) $56,883.8

In this project, site personnel were acquainted to production rate than process duration given the characteristics of work progress measurement used in the project production control. Using the historical data of analyzed processes, objective production rate PDFs for each process were fitted (see PDFs parameters in Table 3). Meetings with project personnel lead to develop a particular simulation solution, where production rate PDFs in simulation models are regarded as processes daily work progress without regard to the number of men working every day.

Step 3: The information gathered from historical data case was not necessarily an accurate representation of the on-site production reality; since the measurements were performed over different time horizons and number of production units for each process. Furthermore, the analysis of relationships between these processes and their IWIPBf sizes did not provide clear information. Then, historical information was only used to construct Production Rate PDFs. To state a base case that will represent real production conditions of a non-buffered production scenario, a simulation model of processes package with MWIP Bf were used. Intermediate and final outputs were examined by site personnel, finding that simulation model was a reliable description of production reality.

Table 3. Production Rate PDFs for Case A.

Process PDF Parameters 1 Exponential Mean=0.596 2 Beta α1= 1.005 α2= 3.353 Minimum= -4.462×10-5 Maximum= 2.638 3 Exponential Mean=0.664 4 Inverse Gaussian μ (β)= 0.509 λ (α)= 3.004 5 Triangular Minimum= 0 Maximum= 2.361 Most Likely= 0

Table 4 shows the main production responses for Base Case A. Average men-day were collected from historical data to estimate labor productivity. The ‘Total Average men-day’ and ‘Total Average Labor Productivity’ rows represent the average value for men-day and labor productivity respectively regarding all processes. Afterward, SO experiments for project objectives were developed according to specifications of methodology showed in Figure 4.

Table 4. Production responses for Base Case A (non-buffered).

P1 P2 P3 P4 P5 TP (units) 32.0 32.0 32.0 32.0 32.0 CT (days) 54.73 60.86 63.38 70.14 69.49 MWIPBf (units) Bf Nº Bf12 Bf23 Bf34 Bf45 Size 0.60 0.60 0.60 0.60 mi (units/day) 0.60 0.53 0.51 0.46 0.46 Standard deviation of mi(units/day) 0.59 0.48 0.64 0.25 0.58 COV of mi (%) 99.06% 90.45% 125.75% 54.58% 125.44% Average men-day (md) 2.77 3.73 3.50 1.12 2.91 Total Average men-day (md) 2.81 Average Labor Productivity (units/md) 0.215 0.142 0.145 0.411 0.159 ATm (units/day) 0.51 Average COV of mi (%) 99.05% Total Average Labor Productivity (units/md) 0.214 TCT for 32 units (days) 80.56 TC ($) 63.086,4

Step 4: Two solutions were obtained through the SO process for each project objective. To filter solutions, 1000 simulations runs were performed for each SO solution obtaining the best solutions showed in Table 5. The best solutions (IWIP Bf size combination) for each project objective are selected in function of its production response. For instance, if the project objective is Min TC, it will be searched the IWIP Bf size combination that has the lesser cost. Table 5 adopts the same names defined in Figure 1 for WIP Bf.

In Case A, decision-makers choose IWIP Bf strategy that will minimize the TCT difference between base and buffered case (marked on bold letters). Demand pressure to finish project on time, leads to decision- makers to choose this solution.

In Table 5, the average of IWIP Bf sizes for Min TCT, Min TC and Max ATm are 2.25 units, 5.75 and 12.75 units respectively, being the location of the IWIP Bf size for Min TC intermediate between Min TCT and Max ATm. Also, IWIP Bf size for Min TC has production responses (time and production rate) located between production responses for Min TCT and Max ATm, confirming theoretical statement addressed in section 6. It is necessary to notice that there is a distinction in the way to compute the ‘difference for Average production rate’ and ∆ATm, since the first one is estimated as the difference between actual and expected (base case), and the last one is the opposite. However, both are focused to maximization of average production rate.

Step 5: Figure 4 describes the construction schedule through LOB and CDF for buffered case. A closer analysis of CDF for buffered case shows that the more expected value for TCT equal to 80.71 days is between 5th percentile equal to 73.10 days and 95th percentile equal to 88.32 days, meaning that the most pessimistic schedule scenario with a 95% of likelihood could exceed to the more expected value only by 9.43% (information about the accurately of simulation forecasting).

Table 5. Best SO solutions for each project objective after 1000 simulation runs in Case A.

Simulation Experiment WIP Bf Strategy WIPBf Size (units) Average Total Cycle Time (days) Average Total Cost ($) Average Production Rate (units/day) WIP Bf1,2 WIP Bf2,3 WIP Bf3,4 WIP Bf4,5 Base Case MWIP Bf 0.6 0.6 0.6 0.6 80,56 63.086,4 0,51 Min TCT IWIP Bf 1 1 1 6 80,71 60.790,6 0,57 Min TC 3 5 4 11 89,83 60.455,7 0,59 Max Atm 13 13 11 14 133,78 64.078,9 0,62 Differences with Base Case Simulation Experiment WIP Bf Strategy WIPBf Size (units) Average Total Cycle Time Average Total Cost Average Production Rate WIP Bf1,2 WIP Bf2,3 WIP Bf3,4 WIP Bf4,5 Min TCT IWIP Bf 1 1 1 6 0,18% -3,64% 10,75% Min TC 3 5 4 11 11,50% -4,17% 16,2% Max Atm 13 13 11 14 66,07% 1,57% 22,05%

Figure 6. Construction Schedule for Buffered Case A: a) LOB and b) CDF.

On-site test: It was necessary to test the methodology robustness at tactical scheduling level, being SO central in the design of WIP Bf. In doing so, construction schedule from Figure 6 was implemented on-site with the support of project personnel, being their respective implemented IWIP Bf sizes: IWIP Bf1,2=1.75 units, IWIP Bf2,3=1.00 units, IWIP Bf3,4=1.40 units, and IWIP Bf4,5=5.50 units.

The data analysis is focused on the impacts of the WIP Bf strategy over the total average labor productivity, TC and production rate variability (COV of mi).  Production rates and cycle times are not analyzed since total average men-day between simulation assumptions based on historical data and on-site implementation experimented an increasing of 10% (from 2.81 md to 3.09 md). This could bias analysis and to hide real improvements.

Figure 7 summarizes improvements on total average labor productivity and TC. Analysis regarding planned estimations on labor productivity and cost are not included due to stochastic and real scenarios always exceeded planned estimations. Then, it is most useful to analyze simulation forecasting on-site.  Figure 7a shows that buffered case increases the average labor productivity on 8.2% in relation of base case. But, on-site implementation shows a higher improvement with an increasing of 11.4% on average labor productivity. Processes are benefitted with a continuous resource utilization through IWIP Bf, mainly process P5 (higher IWIP Bf). This implies reduction of wastes as waiting or idle times. This should be improve project costs, as Figure 7b shows with an forecasted TC increasing of 3.6% in relation of base case, where improvements on labor productivity implies more rational use of resources and reduction on direct costs, mainly.  However, on-site implementation shows better results with an increasing of 15.5% of TC in relation of base case, agreeing with on-site labor productivity improvements.

Figure 7. Global analysis of Total Average Labor Productivity and TC impacts of IWIP Bf implementation for Case A.

Variability levels using Average COV of mi for buffered case show a drop of -10.66% regarding base case, supporting expected lean impacts of buffers over production variability. However, variability levels given the conditions of weather over on-site implementation increase in relation to base case on 3.95%.

## Case Study B

Step 1 and 2: Table 6 shows the planned schedule parameters and total costs of selected processes package. Equipment and supervision costs are not regarded. The MWIPBf size is equal to 0.6 units. It is necessary to notice that two kinds of processes duration were used according to site personnel opinion (given the lack of historical data): units type 1 and units type 2. The first 20 units were regarded type 1 and the last 10 units type.  In this case, site personnel were acquainted with process duration by unit. Table 7 describes the process duration PDF developed from expert judgement using VIBES.

Step 3: Due to the lack of historical data and similarly to Case A, a simulation model of processes package with MWIP Bf were used as a non-buffered base case. Expert judgement of site personnel was used to validate intermediate and final simulation outputs. Table 8 shows the main production responses for Base Case B, similarly to Case A in Table 4. Average men-day were estimated from expert judgement. Later, SO experiments were developed.

Table 6. Planned Production and Cost Parameters for Case B.

Planned Production Parameters and Direct Costs Planned Indirect Costs Process Type of Process MUCi ($/unit) TP (units) mi (units/day) CTi (days) LDCi ($/day) DC ($) DOC ($/day) TCT (days) Overhead (US$) P1 DryWall Ceeling $94,4 20 1 20 $85,0 $3.588,8 $58,0 35 $2.030,0 $87,6 12 1 12 $78,8 $1.997,4 Total (2) $2.030,0 P2 Partition-1st Layer $123,3 20 1 20 $111,0 $4.685,7 $106,3 12 1 12 $95,7 $2.424,7 P3 Plumbing and Electrical Installation $170,4 20 1 20 $153,4 $6.476,8 $156,6 12 1 12 $140,9 $3.570,6 Total (1) + (2) $31.173,3 P4 Partition-2nd Layer $111,0 20 1 20 $99,9 $4.217,2 $95,7 12 1 12 $86,1 $2.182,2 Total (1) $29.143,3

Table 7. Process Duration PDF for Case B.

Home Type 1 Home Type 2 Process Nº Min (days) Max (days) Shape Parameter "α" Shape Parameter "β" Min (days) Max (days) Shape Parameter "α" Shape Parameter "β" 1 0,33 1,00 1,00 3,25 0,83 1,50 1,00 3,25 2 0,50 1,00 1,00 3,32 1,00 1,50 1,00 3,32 3 0,50 1,25 1,38 1,19 1,00 1,75 1,38 1,19 4 0,50 1,00 1,00 3,32 1,00 1,50 1,00 3,32

Step 4: Table 9 shows best solutions for IWIP Bf size combination selected according to specifications of methodology showed in Figure 4. Similarly to reasons stated for Case A, decision-makers choose IWIP Bf strategy that will minimize TCT difference between base and buffered case (marked on bold letters). Also, the average IWIP Bf size for Min TC (16.0 units) is in-between Min TCT (5.0 units) and Max ATm (25.7 units) according to their production responses.

Step 5: Figure 8 describes the construction schedule through LOB and CDF for buffered case. Analysis of CDF for buffered case shows that the more expected value for TCT equal to 27.48 days is between 5th percentile equal to 25.00 days and 95th percentile equal to 29.48 days, meaning that the most pessimistic schedule scenario with a 95% of likelihood could exceed to the more expected value only by 7.2%.

On-site test: Similarly Case A, an on-site implementation of buffered construction schedule of Figure 8 was developed. The implemented IWIP Bf sizes were: IWIP Bf1,2=1.65 units, IWIP Bf2,3=2.40 units, and IWIP Bf3,4=8.80 units.

Table 8. Production responses for Simulated Base Case B with MWIPBf.

P1 P2 P3 P4 TP (units) 32,0 32,0 32,0 32,0 CT (days) 25,52 25,41 26,30 26,17 MWIPBf (units) Bf Nº Bf12 Bf23 Bf34 Size 1,00 1,00 1,00 mi (units/day) 1,26 1,26 1,22 1,23 Standard deviation of mi(units/day) 0,67 0,69 0,65 0,67 COV of mi (%) 53,19% 54,90% 53,52% 54,86% Average men-day (md) 2,00 6,00 4,00 6,00 Total Average men-day (md) 4,50 Average Labor Productivity (units/md) 0,628 0,210 0,305 0,204 ATm (units/day) 1,24 Average COV of mi (%) 54,12% Total Average Labor Productivity (units/md) 0,337 TCT for 32 units (days) 27,57 TC ($) 27.894,9

Table 9. Best SO solutions for each project objective after 1000 simulation runs in Case B.

Simulation Experiment WIP Bf Strategy WIPBf Size Average Total Cycle Time (days) Average Total Cost ($) Average Production Rate (units/day) WIP Bf12 WIP Bf23 WIP Bf34 Base Case MWIP Bf 1 1 1 27.57 27,894.9 1.24 Min TCT IWIP Bf 1 1 13 27.50 27,127.8 1.37 Min TC 24 1 23 41.25 25,288.8 2.20 Max ATm 28 21 28 55.85 26,105.20 2.22 Differences with Base Case Simulation Experiment WIP Bf Strategy WIPBf Size Average Total Cycle Time Average Total Cost Average Production Rate WIP Bf12 WIP Bf23 WIP Bf34 Min TCT IWIP Bf 1 1 13 -0.25% -2.75% 10.21% Min TC 24 1 23 49.65% -9.34% 77.23% Max ATm 28 21 28 102.61% -6.42% 78.93%

This case did not have the same conditions that Case A, being validate comparisons of the different production scenarios without any filter. TCT for buffered case showed in Figure 8 is lightly better to base case with a difference of -0.3%.  On-site implementation of buffered construction schedule also showed a light difference in relation to base case of 1.6%, being forecasting of simulated buffered case a good description of production reality. However, impacts on project performance were focused on labor productivity, cost and variability due to total average men-day between simulation assumptions based on expert judgement and on-site implementation experiment an increasing of 13.0 % (from 4.5 md to 5.09 md). Furthermore, there was under confidence of project expert to estimate planned production responses (See Table 1 and 6), being increased during simulation and on-site experimentations. Given this reason, planned production responses were not used to make comparisons, and the comparison basis is the base case.

Figure 8. Construction Schedule for Buffered Case A: a) LOB and b) CDF.

Figure 9 summarizes improvements on total average labor productivity and TC. As Case A, Figure 9a shows improvement for labor productivity in buffered case against base case equal to 6.35%. On-site implementation shows better improvements against base case equal to 11.4%. In spite of the average on-site IWIP Bf size was lesser than estimation of buffered case (4.28 units against 5 units, respectively), the labor productivity improvement was better than expected (given the impact on continuous resource utilization, mainly in process P4 where the IWIP Bf size is the highest). Accordingly, impacts on TC were beneficial in buffered case and on-site implementation with improvements of -2.75% and -10.59% against base case. Poor cost results on buffered case could be explained by the cost frame, where the most buffered process was P4 meaning better productivity. However, P4 was one the process with less incidence on direct cost (22.1%), implying light impacts on total costs (keeping constant indirect cost given the variation of TCT on all scenarios).

On the other hand, the average COV of mi is increased for buffered case and on-site implementation up to 12.34% and 44.34% respectively, in relation to case base. The main reason is the high variability level increasing on the process P4. In contrast, remaining processes tend to keep variability levels. In addition, P4 has the higher mi due to the IWIP Bf size impact (8.80 units) inducing high levels of production rates for units type 1 (having, also, the faster production rate according to duration PDF from Table 7) and normal levels of production rates for units type 2. This range of production rate levels between units type 1 and 2 produces higher level of buffered and on –site COV for mi.

Figure 9. Global analysis of Total Average Labor Productivity and TC impacts of IWIP Bf implementation for Case B.

## Strategic Level Application

At this level, an example of project scheduling is used to apply methodology to design IWIP Bf. Figure 10 shows analyzed processes through a scheduling network of a repetitive building project. The expected duration for each process is 2 days by production unit and the MWIP Bf is 1 unit. The remaining expected or planned production parameters and project costs are described in Table 10.

Figure 10. Construction Schedule at strategic level.

Table 10.  Planned Production and Cost Parameters for Project Example.

Planned Production Parameters and Direct Costs Planned Indirect Costs Number of processes TP (units) mi (units/day) CTi (days) MUCi ($/unit) LDCi ($/day) EqDCi ($/day) DC ($) TCT (days) SPCi ($/unit) DOC ($/day) IC ($) 23 100 0.5 200 $450.0 $45.0 $120.0 $1,794,000.0 218 700 $390.0 $101,120.0 Total (1) $1,794,000.0 Total (2) $101,120.0 a Approximated Budget in U.S. dollars for analyzed processes package. Total (1) + (2)a $1,895,120.0

Step 1: Processes on Critical Path from Figure 10 were chosen to develop SO process. Using Beta PDF for process duration, abacus for four levels of variability measured through COVD were developed.

Figure 11. Abacus for Pareto Front Line for 10 repetitive processes, with an expected duration by unit of 2 days: a) COVD=25%, b) COVD=50%, c) COVD=75%, and d) COVD=98%. IWIP Bf sizes are production units.

This variability levels were 25%, 50%, 75% and 98% keeping an average duration by unit of 2 days (due to mathematical nature of Beta PDF, the highest level of variability was 98%). Once extreme points in the abacus for each variability level were defined, intermediate points (IWIP Bf sizes) were determined. Final responses over ∆ATm and ∆TCT were computed and Pareto Front Line with IWIP Bf sizes were stated (Figure 11). Each abacus has two mathematical expressions. The first one allows to describe the relationship between ∆ATm and ∆TCT. The second one allows to determine the IWIP Bf size once ∆ATm and ∆TCT were defined (according project preferences). Coefficient of determination (R2), Standard Error and P-value (at α level=0.05) are statistical measurements used to show the good quality of mathematical expressions described in Figure 11. Additionally to expression relating ∆ATm and ∆TCT, the user could utilize graphically abacus to define the levels of any of these variables.

Step 2: For this example, it is estimated that processes could reach variability levels of 50% during execution phase, so that, abacus from Figure 11b is used. Using points (IWIP Bf) addressed in the step 1 and showed in Figure 11b, a sensitivity analysis is develop.  Actual ATm, TCT and TC are computed for each IWIP Bf based on equations 6, 7 and 11. Sensitivity results are showed in Table 11.

Table 11. Sensitivity Analysis to choose optimum IWIP Bf size.

WIP Bf (units) ∆ATm ∆TCT Actual ATm (units/day) Actual TCT (days) Actual TC ($) 1 11.49% 18.36% 0.44 258.0 $2,009,216.4 4 3.81% 25.98% 0.48 274.6 $1,947,260.5 8 0.81% 58.71% 0.50 346.0 $1,951,266.7 12 0.06% 90.85% 0.50 416.1 $1,972,810.7 16 -0.16% 124.09% 0.50 488.5 $1,999,392.0 20 -0.32% 157.03% 0.50 560.3 $2,026,230.6

Step 3: In this case, a decision-maker could be interested into minimize project cost. Then, the optimum WIP Bf sizes is equal to 4 units (See Table 11).

Step 4: As Case A and B, a construction schedule is defined considering the size of IWIP Bf.

Project Example Test: Processes network showed in Figure 10 was simulated, taking into account two scenarios: a real case without buffer (WIP Bf size equal to 1 unit) and a buffered case. The processes duration PDFs are showed in Table 12. After 1000 simulation runs for each scenario, the results of a hypothetic implementation of WIP Bf on a repetitive building project at strategic level can be seen in Table 13.

Table 12. Duration PDFs for Project Example.

Processes Average duration by unit (days) COV of Duration by unit (%) PDF Type PDF Parameters P1,…,P10 2.2 57.72 Beta a=1.01 b=1.01 L=0 U=4.4 P11,…,P18 2.15 57.74 Uniform a=0 b=4.3 P19,…,P23 2.2 56.36 Gama α=3.17 β=0.694

Table 13. Project Performance results for Strategic WIP Bf Implementation.

WIP Bf (units) ∆ATm ∆TCT ∆TC 1 19.67% 36.44% 11.72% 4 13.61% 44.37% 8.41%

Table 13 indicates improvement on cost using IWIP Bf size equal to 4 units (it decreases impacts of variability on project cost). It is interesting to comment that variability levels and processes duration for real production situations (without and with buffer) were higher than abacus (Figure 11b). This non-favorable situation does not cancel the beneficial impacts of WIP Bf over variable production scenarios.

# Conclusions

This research has showed the feasibility to apply WIP Bf strategies in construction project, in order to decrease the negative impacts of variability in production processes and to increase project performance. Two levels for designing WIP Bf were proposed within the construction scheduling process. These levels were tactical and strategic. At tactical level, SO process was applied being a central part of the proposed methodology. Also, SO is suitable to several production situations for medium-term period in construction projects. Two case studies were implemented at this level, allowing different levels of performance improvement with the application of WIP Bf strategies. However, the magnitude of the improvements depends on the context of application (season of the year, execution complexity, kind of processes, nature of project organization, variability levels, modeling assumptions, among others), the concern of project decision makers and site personnel to use production strategies based on WIP Bf, and the control level of external problems (e.g., material or labor supply). Perhaps, one of the factors most important for a successful implementation of WIP Bf is the commitment of the project organization (from project managers to subcontractors). This research is part of an ongoing research over the topic of buffer management and these two case studies depicts only a part of other failed project implementations where the organization commitment was low and the external problems were plentiful. At strategic level, methodology demonstrated that can be useful to reduce inter-dependence between processes for a given level of variability, resulting on project performance improvements (as project example, on project costs). Furthermore, the notion of dynamic and variable nature of production processes in construction is highlighted in the methodology.

The proposed methodology reduces the management cost and supervision effort of labor, due to labor permanency on-site is decreased and its efficiency is increased. Other benefits are related to the subcontractor efficiency. While increases the labor efficiency, reduces its permanency in-site and labor can be used in other project and subcontractor increases its profits. Methodology also contributes to reduce waste in-site decreasing waiting times and stimulating a continuum work flow. Besides, it contributes to add-value decreasing rework by assuring the quality of WIP for downstream crews.

The WIP Bf design methodology also showed that simple, sound and practical approaches can be developed to solve the variability problem in construction, being the proposed SO frame and multiobjective models an example of this.  Mainly, the latter is the first approach to generalize the application of WIP Bf in construction through simple means. This should facilitate its penetration in construction industry and should contribute to shorten the gap between theory and practice in the knowledge body of buffer management. While there is variability in construction, more rational use of buffers will be necessary.

The paper is part of an ongoing research to generalize and model WIP Bf in repetitive projects. The following step is to finish the logic sequence of WIP Bf methodology development with the WIP Bf management at operational level (not only scheduling, but also planning and control). Currently, it is carrying out the development and investigation of decision-making models to forecast and control more efficiently and rationally on-site production in construction, including the management of WIP Bf designed at upper production levels. Next articles will address broadly this topic.

REFERENCES

AbouRizk, S. M., Halpin, D. W. and Wilson, J. R. (1991). “Visual Interactive Fitting of Beta Distributions”. J. Const. Engrg. and Mgmt., ASCE, vol 117, n° 4, pgs. 589-605.

Agbulos, A. and AbouRizk S. M. (2003). An Application of Lean Concepts and Simulation for Drainage Operations Maintenance Crews. Proceedings of Winter Simulation Conference, !!!!!!

Alarcón, L.F. and Calderón, R. (2003). Implementing Lean Production Strategies in Construction Companies. Proceedings Construction Research Congress, Winds of Change: Integration and Innovation of Construction, ASCE, March 19-21, Honolulu, Hawaii.

Alarcón, L.F., Diethelm, S., Rojo, O. and Calderón R. (2005). Assesing the Impacts of Implementing Lean Construction. Proceedings of IGLC-13, Sidney, Australia, July.

Alarcón, L.F. and Ashley, D. B. (1999). Playing Games: Evaluating the Impact of Lean Production Strategies on Project Cost and Schedule. Proceedings of IGLC-7, University of Berkeley, California, U.S.A., 26-28 July.

Al-Battaineh, H. T. and AbouRizk S. M. (2006). Productivity Simulation During The Planning Phase of The Glencoe Tunnel in Calgary, Canada: A Case Study. Proceedings of Winter Simulation Conference, !!!!!!!!!!!

Alves, T. and Tommelein, I.D. (2004). Simulation of Buffering and Batching Practices in the Interface Detailing-Fabrication-Installation of HVAC Ductwork. Proceedings of IGLC-12, August, Elsinore, Denmark.

Alves, T. and Tommelein, I.D. (2003). Buffering and Batching Practices in la HVAC Industry. Paper presented to eleventh Annual Conference of International Group for Lean Construction, Virginia Tech, Blacksburgh, Virginia, U.S.A, 16-17 July.

Arbulu, R., Ballard, G. and Harper, N. (2003). Kanban in Construction. Proceedings of IGLC-11, Virginia Tech, Blacksburgh, Virginia, U.S.A, 16-17 July.

Arbulu, R. and Tommelein, I.D. (2002). Contributors to Lead Time in Construction Supply Chains: Case of Pipe Supports Used in Power Plants. Proceedings of Winter Simulation Conference, San Diego, California, USA, December 8-11.

APICS (1995). Dictionary. Eighth Edition.

Ballard, G. (2000). The Last Planner System of Production Control. Ph.D. Dissertation, School of Civil Engineering, Faculty of Engineering, The University of Birmingham, Birmingham, U.K.

Ballard, G. and Howell, G. (1998). Shielding Production: Essential Step in Production Control. J. Const. Engr. Mgmt., ASCE, Vol. 124, N° 1, pp. 11-17.

Bashford, H. H., Sawhney, A., Walsh, K. D. and Kot, K. (2003). Implications of Even Flow Production Methodology for U.S. Housing Industry. J. Const. Engr. Mgmt., ASCE, Vol. 129, N° 3, pp. 330-337.

Bertelsen, S. (2003). Complexity – Construction in a New Perspective. Proceedings of IGLC-11, Virginia Tech, Blacksburgh, Virginia, U.S.A, 16-17 July.

Bing, L., Lee-Kong-Tiong, R., Wai Fan, W. and Chew, D. (1999). Risk Management in International Construction Joint Ventures.  J. Const. Engr. Mgmt., ASCE, Vol. 125, N° 4, pp. 277-284.

Buchholz and Thümmler (2005). Enhancing Evolutionary Algorithms with Statistical Selection Procedures for Simulation Optimization. Proceedings of Winter Simulation Conference, Orlando, Florida, USA, December 4-7.

Carson, Y. and Maria, A. (1997). Simulation Optimization: Methods and Applications. Proceedings of Winter Simulation Conference, Atlanta, Georgia, USA, December 7-10.

Construction Industry Institute, CII, (1988). Project Materials Management Primer. RS47-1, Prepared by the Material Management Task Force, Austin, Texas.

Extend v6 User’s Guide (2002). Manual User. Imagine That Inc.

Feng, C., Liu, L. and Burns S. (1997). Using Genetic Algorithms to Solve Construction Time-Cost Trade-Off Problems. J. Comp. Civ. Engr., ASCE, Vol 11, N° 3 pp. 184-189.

Fente, J., Knutson, K. and Schexnayder, C. (1999). Defining a Probability Distribution Function for Construction Simulation. Proceedings of Winter Simulation Conference, Point Hilton Squaw Peak Resort, Pheoenix Az, U.S.A., December.

Ford, D. N. (2002). Achieving Multiple Project Objectives through Contingency Management. J. Const. Engr. Mgmt., ASCE, Vol 128, N° 1, pp. 30-39.

González, V., Alarcón, L.F. and Gazmuri, P. (2006). Design of WIP Buffers in Repetitive Projects: A Study Case. Paper presented to 14th Annual Conference of International Group for Lean Construction, Santiago, Chile, July 25th – 27th.

González, V., Rischmoller, L. and Alarcón, L.F. (2004). Design of Buffers in Repetitive Projects: Using Production Management Theory and IT Tools. 4th International Postgraduate Research Conference, University of Salford, Manchester, U.K., April 1st –2nd.

Goldratt, E. M., (1997). Critical Chain. North River Press, Great Barrington, Massachusetts, 246 pp.

Ipsilandis, P. G. (2007). Multiobjective Linear Programming for Scheduling Linear Repetitive Projects. . J. Const. Engrg. and Mgmt., ASCE, vol. 133, n° 6, pgs. 417-424.

Halpin, D. W. (1977). CYCLONE: Method for modeling job site processes. J. Constr. Div., vol.  103, nº 3, pgs. 489-499.

# Hendrickson, C. and Au, T. (1989). Project Management for Construction: Fundamental Concepts for Owners, Engineers, Architects, and Builders. Prentice Hall, Englewood Cliffs, 537 pgs.

Hopp, W. J. and Spearman, M. L. (2000). Factory Physics: Foundations of Manufacturing Management. Irwin/McGraw-Hill, Boston, 668 pgs.

Hooper, J. W. (1986). Strategy Related Characteristics of Discrete-Event Languages and Models. Simulation, 46(4), 153-159.

Horman, M. J. (2000). Process Dynamics: Buffer Management in Building Project Operations. Ph D Dissertation, Faculty of Architecture, Building and Planning, The University of Melbourne, Melbourne, Australia.

Howell, G., Ballard, G. and Hall, J. (2001). Capacity Utilization and Wait Time: A Primer for Construction. Proceedings of IGLC-9, Singapore, Korea.

Howell, G., Laufer, A. and Ballard, G. (1993). Interaction Between Subcycles: One Key to Improved Methods. J. Const. Engr. Mgmt., ASCE, Vol. 119, N° 4, pp. 714-728.

Kim, K. and De la Garza, J. M. (2003). Phantom Float. J. Const. Engr. Mgmt., ASCE, Vol. 129, N° 5, pp. 507-517.

Koskela, L. (2000). An Exploration Towards a Production Theory and its Application to Construction. Ph. D. Dissertation, VTT Building Technology, Helsinki University of Technology, Espoo, Finland.

Laufer, A., Tucker, R. L., Shapira, A. and Shenhar R, A. J. (1994). The Multiplicity Concept in Construction Project Planning. Construction Management and Economics, Vol 12, Nº1, pp. 53-65.

Law A. M. and Kelton W. D. (2000). Simulation Modeling and Analysis, 3rd Ed. McGraw-Hill, New York, 760 pgs.

Lee, S., Peña-Mora, F. and Park M. (2003). Reliability and Stability Buffering Approach in Concurrent Design and Construction Projects. Proceedings of IGLC-11, Virginia Tech, Blacksburgh, Virginia, U.S.A, 16-17 July.

Leach, L. P.  (2003). Schedule and Cost Buffer Sizing: How Account for the Bias Between Project Performance and Your Model. Proj. Mgmt. J., Vol. 34, N° 2, pp. 34-47.

Martínez, J.C. (1996). STROBOSCOPE: State and Resource Based Simulation of Construction Processes. PhD Dissertation, University of Michigan, East Lansing, U.S.

McGray, G. E., Purvis, R. L. and McCray, Coleen G. (2002). Project Management Under Uncertainty: The Impact of Heuristics and Biases. Proj. Mgmt. J., Vol. 33, N° 1, pp. 49-57.

Park M. and Peña-Mora, F. (2004). Reliability Buffering for Construction Projects. J. Const. Engrg. and Mgmt., ASCE, vol 130, n° 5, pgs. 626-637.

Polat, G., Arditi, D. and Mungen, U. (2007). Simulation-Based Decision Support System for Economical Supply Chain Management of Rebar. J. Const. Engr. Mgmt., ASCE, Vol 133, N° 1, pp. 29-39.

Rojas, E. M. and Aramvareekul, P. (2003). Labor Productivity Drivers and Opportunities in the Construction Industry. J. Mgmt. Engr., ASCE, Vol. 19, N° 2, pp. 78-82.

Shen, L.J. and K. H. Chua, D. (2005). Impact of Variability on Construction Schedules. Proceedings of IGLC-13, Sidney, Australia, July.

Srisuwanrat, C., and Ioannou, P. (2007). The Investigation of Lead-Time Buffering Under Uncertainty Using Simulation and Cost Optimization. Paper presented to 15th Annual Conference of International Group for Lean Construction, East Lansing, Michigan, U.S., July.

Thomas, H. R. and Arnold, T.M. (1996). Overmanning and the Effects on Labour. Proceedings of the CIB W65 International Symposium for the Organization and Management Construction, University Strathclyde, pp. 39-48.

Tommelein, I. D., Riley, D. R. and Howell G. A. (1999). Parade Game: Impact of Work Flow Variability on Trade Performance. J. Const. Engr. Mgmt., ASCE, Vol 125, N° 5, pp. 304-310.

Tommelein, I. D. (1998). Pull-Driven Scheduling for Pipe-Spool Installation: Simulation of Lean Construction Technique. J. Const. Engr. Mgmt., ASCE, Vol. 124, N° 4, pp. 279-288.

Vanegas, J. A., Bravo. E. B. and Halpin, D. W. (1993). Simulation Technologies for Planning Heavy Construction Processes. J. Const. Engr. Mgmt., ASCE, Vol. 119, N° 2, pp. 336-354.

Walsh, K. D., Sawhney, A. and H. H. Bashford (2007). Production Equation for Unsteady-State Construction Processes. J. Const. Engr. Mgmt., ASCE, Vol. 133, N° 3, pp. 254-261.

Walsh, K. D., Hershauer, J., Walsh, T., Tommelein I. and Sawhney, A. (2002). Lead Time Reduction Via Pre-Positioning of Inventory in an Industrial Construction Supply Chain. Proceedings of Winter Simulation Conference, San Diego, California, USA, Dec. 8-11.

Womack, J. P. and Jones, D. T. (1996). Lean Thinking: Banish Waste and Create Wealth in Your Corporation. Simon & Schuster, New York, N.Y., 350 pp.

Yang, I. (2005). Chance-Constrained Time-Cost Tradeoff Analysis Considering Funding Variability. J. Const. Engr. Mgmt., ASCE, Vol. 131, N° 9, pp. 1002-1012.

Zheng, D. X. and Thomas, S. (2005). Stochastic Time-Cost Optimization Model Incorporating Fuzzy Sets Theory and Nonreplaceable Front. J. Const. Engr. Mgmt., ASCE, Vol. 131, N° 2, pp. 176-186.

Zheng, D. X., Thomas, S. and Kumaraswamy, M. M. (2005). Applying a Genetic Algorithm-Based Multiobjective Approach for Time-Cost Optimization. J. Const. Engr. Mgmt., ASCE, Vol. 130, N° 2, pp. 168-176.

# Footnotes

M. Eng., Ph. D. Candidate, School of Engineering, Department of Construction Engineering and Management, Pontificia Universidad Católica de Chile, Postal Code 7820436, Santiago, Chile, Phone (562)3544245. Lecturer, Construction Engineering School, Universidad de Valparaíso, Chile, vagonzag@uc.cl

Professor, School of Engineering, Department of Construction Engineering and Management, Pontificia Universidad Católica de Chile, Postal Code 7820436, Santiago, Chile, Phone (562)3544245, lalarcon@ing.puc.cl

Lean production is a management philosophy focused on adding value from raw materials to finished product. It allows avoiding, eliminating and/or decreasing waste from this so-called value stream. Among this waste, production variability decreasing is a central point within the Lean philosophy from a system standpoint (Womack and Jones 1996).

# Text boxes

a) COVD=25%

D

b) COVD=50%

c) COVD=75%

d) COVD=98%

IWIP Bf= 1

IWIP Bf= 3

IWIP Bf= 5

IWIP Bf= 7

IWIP Bf= 9

IWIP Bf= 11

IWIP Bf= 4

IWIP Bf= 8

IWIP Bf= 12

IWIP Bf= 16

IWIP Bf= 20

IWIP Bf= 1

IWIP Bf= 6

IWIP Bf= 12

IWIP Bf= 18

IWIP Bf= 1

IWIP Bf= 24

IWIP Bf= 7

IWIP Bf= 14

IWIP Bf= 21

IWIP Bf= 28

IWIP Bf= 35

IWIP Bf= 1

R2=0.999         Standard Error=0.120

R2=0.987         P-value=0.001

R2=0.996         Standard Error=0.447

R2=0.999         P-value=0.00001

R2=0.998         Standard Error=0.002

R2=0.998         P-value=0.002

R2=0.994         Standard Error=1.02

R2=0.989         P-value=0.001

∆

∆

∆

∆